## Sheet1
COSC1076 ¦ Semester 1 2021
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name:
Group Member: | Alasdair |  | Progress Classes: | Ahead
Group Member: | Abu Kuhafa |  |  | On-track
Group Member: | Sithira |  |  | Behind
Group Member: | Hibbaan |  |  | Way Behind
Tutor:
Class:
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | Alasdair | Abu Kuhafa | Sithira | Hibbaan
|  |  | Group Formed | yes | Weekly Contribution
|  |  | MS Team created | yes | Issues
|  |  | Git Repo created | yes | Other Notes
|  | Progress | On-track
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | Alasdair | Abu Kuhafa | Sithira | Hibbaan
|  |  | Choice of where to use linked list, vector & array |  | Weekly Contribution | Put forward draft design.
|  |  | Initial Design of ADTs (classes and potential methods) |  | Issues
|  |  | Main menu |  | Other Notes
|  |  | User Prompt (for gameplay), but no/minimal error checking |  |  | All agreed with initial design. | Main menu |  | User Prompt implementation had been started
|  |  | Linked List implementation |  |  |  | Progressing on LinkedList
|  |  | Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required |  |  | ADT implementations | ADT implementations | ADT implementations | ADT implementations
ADT implementation for storing information, game loop logic not required
|  | Progress | On-track
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates | A | B | C | D
|  |  | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) |  | Weekly Contribution | Load/Save, Intialisation of data stuctures, implementaiton of the gamengine | Test Cases, tilebag randomization | Test Cases | Implemntation of board progression
|  |  | Initialisation of data structures for new game |  | Issues |  |  |  | Issue: implementing a legally placing method
|  |  | Write Tests Cases for common uses |  | Other Notes
|  |  | Gameplay for single round, that is selecting and moving of tiles from a factory to players mosaic |  | The progression was behind as the team needed to resolve some of the issues first before they were able to play the game for a single round.
|  | Progress | Behind
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates | A | B | C | C
|  |  | Fully complete implementation and error free |  | Weekly Contribution | Final Tests | Final Tests, Group Reprot | Final Tests | Final Tests
|  |  | Full error checking of user prompt |  | Issues |  | Issue: tilebag creation
|  |  | Automated placement of tiles at end of round, but no scoring |  | Other Notes
|  |  | Final Tests |  |  | fully complete implementaion of gameEngine |  |  | fully complete implementation of te board
|  |  | Group Report Written |  |  | error checks |  |  | error checks
|  | Progress | On-track